## WBS Tracker
Project | Module | Sub-Module | Page / Functionality Check | Scope of Check | Estimation Rationale | Estimated Hours | Actual Hours | Date Worked | Status | Variance (h) | Remarks
Progbiz ERP | CRM | Login | Login page functionality | Form load, valid/invalid login, Enter-key submit, password eye toggle, Forgot Password, redirect to home | 8 small checks; static form, no data setup | 2 |  |  | Pending
Progbiz ERP | CRM | Homepage | Home dashboard checks | Greeting, count cards, Create New menu, Today's Schedule, timeline/calendar entry points | Read-only verification; no forms | 2 |  |  | Pending
Progbiz ERP | CRM | Enquiry | Add Enquiry form | Branch/date/auto-number/source fields, customer phone search, New Customer modal, Assign-To, item add (single+multiple), save/cancel | Largest form; AJAX modal + item picker need per-field checks | 4 |  |  | Pending
Progbiz ERP | CRM | Enquiry | Conditional field logic | Followup Status options; Lead Quality shows only for In-Followup; Description for Won/Lost; Next-followup date rules | 4 status paths x field-visibility matrix | 2 |  |  | Pending
Progbiz ERP | CRM | Enquiry | Enquiry Overview page | Details display (customer/status/value/items), actions: Followup, Create Quotation, edit/delete rules before/after followup | State-dependent rules need seeded enquiries in 2 states | 3 |  |  | Pending
Progbiz ERP | CRM | Leads Listing | Leads list & tabs | New/In-Followup/Won/Lost tabs + counts, filters, search, row actions, drill-down | 4 tabs x filter combinations; count integrity vs data | 3 |  |  | Pending
Progbiz ERP | CRM | Follow-up | Follow-up modal | Open, auto date, status options, conditional Lead Quality/Description, business value, save/cancel | Same conditional matrix as enquiry + history write | 3 |  |  | Pending
Progbiz ERP | CRM | Follow-up | Follow-up history rules | Appears in history, latest editable/deletable, older read-only | Needs 2+ followups seeded per lead | 1.5 |  |  | Pending
Progbiz ERP | CRM | Followups Listing | Followups list & tabs | Today's/Delayed/Upcoming/Non-Followup tabs + counts, filters, row Followup action | 4 tabs; date-bucketing correctness needs dated data | 2.5 |  |  | Pending
Progbiz ERP | CRM | Quotation | Create quotation from enquiry | Auto-fill check (all fields except Valid-Upto), items carried, editable after autofill, save to overview | Field-by-field autofill verification | 3 |  |  | Pending
Progbiz ERP | CRM | Quotation | Quotation calculations | Rate x qty gross, discount incl/excl tax, tax, total payable; terms & conditions save | Arithmetic verification across item combinations | 3 |  |  | Pending
Progbiz ERP | CRM | Quotation | Quotation overview & actions | Overview display, View Enquiry/View Quotation, edit, follow-up from quotation | Cross-navigation checks | 2 |  |  | Pending
Progbiz ERP | CRM | Lead Transfer | Lead transfer flow | Filters, lead select, executive pick, transfer, assignee change verification | End-to-end with verification query; backend flaky = buffer | 2 |  |  | Pending
Progbiz ERP | CRM | Settings | Lead Sources master | Create, duplicate rejection, edit, delete, list/search | Simple CRUD master | 1.5 |  |  | Pending
Progbiz ERP | CRM | Settings | Lead Followup Status master | Create with Nature mapping (In-Followup/Won/Lost), edit, delete | CRUD + nature-mapping effect on lifecycle | 1.5 |  |  | Pending
Progbiz ERP | CRM | Item Master | Item create & validations | Mandatory name/variant, blank/whitespace rejection, duplicate rejection, multi-field create | Form + 4 negative paths | 2 |  |  | Pending
Progbiz ERP | CRM | Item Master | Item list operations | Search, edit, delete (if enabled), cancel, category link | List ops; tenant-dependent delete | 1.5 |  |  | Pending
Progbiz ERP | CRM | CRM Dashboard | Reports & summary integrity | Widgets load, filters (period/type/status/source/quality), summary counts vs leads listing parity | Cross-checking numbers across pages is slow, manual | 4 |  |  | Pending
Progbiz ERP | CRM | Customers | Customer listing & detail | List, search modes, filters, detail view, lead-stage display | Read-heavy; several filter modes | 2 |  |  | Pending
Progbiz ERP | Task Management | Home Dashboard | Task cards & sections | Pending/Delayed/Completed/Unscheduled cards, Today's Schedule, Running/On-Hold sections, live timer display | Counts vs list parity + timer observation | 2.5 |  |  | Pending
Progbiz ERP | Task Management | Add Task | Instant task (modal) | Create New->Task, branch/type/priority/task/description/party/participants, save, appears on home + My Tasks | Full modal pass + 2-page verification | 2.5 |  |  | Pending
Progbiz ERP | Task Management | Add Task | Task for Later (scheduled) | Host field & user toggle list, deadline/end-time toggles, date+time set, save, calendar/timeline presence | Host picker + schedule fields + 2-view verification | 2.5 |  |  | Pending
Progbiz ERP | Task Management | Add Task | Repeat (recurring) task | Daily/Weekly/Monthly recurrence, start/end time, from/to date, save, occurrence check | 3 recurrence types; occurrence validation next-day | 2.5 |  |  | Pending
Progbiz ERP | Task Management | Add Task | Validation & negatives | Missing task type, missing title, invalid schedule times, clear button | 4 negative paths, inline messages | 1.5 |  |  | Pending
Progbiz ERP | Task Management | My Tasks | List, tabs & search | Today/Delayed/Upcoming/Unscheduled/Completed tabs + counts, columns, search, row actions | 5 tabs x count/content parity | 2.5 |  |  | Pending
Progbiz ERP | Task Management | Delegated Tasks | Delegated list checks | Columns incl. Assignees, status reflection after assignee actions, date filter | Needs actions performed by another user to verify | 2 |  |  | Pending
Progbiz ERP | Task Management | Created Tasks | Created list & actions | Columns, self vs other-user tasks routing, View/Delete rules (no delete after start) | Routing rules need 2 task ownerships | 2 |  |  | Pending
Progbiz ERP | Task Management | Unscheduled Tasks | Unscheduled page actions | List/columns, Edit, Schedule (moves to scheduled), Start Now, Delete | 4 row actions each with state verification | 2.5 |  |  | Pending
Progbiz ERP | Task Management | Task Details | Notes & documents | Open details panel, add note (Enter=paragraph), send note, upload image/doc/audio/video, activity log | 4 upload types + note behaviour | 2.5 |  |  | Pending
Progbiz ERP | Task Management | Task Details | Edit / Reschedule / Add Lead | Kebab menu: Edit task fields persist, Reschedule date/time updates calendar+timeline, Add Lead opens prefilled enquiry | 3 flows with cross-page verification | 2.5 |  |  | Pending
Progbiz ERP | Task Management | Lifecycle | Start-Hold-Resume-End | Start, Hold (confirm+time window), timer pause, Resume, End, moves between sections, single-active-task rule | Most complex flow; time-window rules + known concurrency bug area | 4 |  |  | Pending
Progbiz ERP | Task Management | Calendar | Calendar checks | Scheduled task on correct date/time, updates after reschedule, admin view of participants | Date-navigation heavy | 2 |  |  | Pending
Progbiz ERP | Task Management | Timeline | Timeline checks | Started/finished/held statuses on history, unscheduled-started status correctness | Known bug area (status display) - re-verify | 2 |  |  | Pending
Progbiz ERP | Task Management | Daily Activity Report | Report checks | All-user rows, durations (running vs hold vs completed), date/user filters | Duration correctness needs timed tasks | 2 |  |  | Pending
Progbiz ERP | Task Management | Multi-user | Cross-user visibility | Host-assigned & participant tasks visible to assignee; admin calendar/timeline oversight | Requires 2nd login + task seeding both directions | 3 |  |  | Pending
Progbiz ERP | Master | Business Contacts | Business contacts master (/business-contacts) | List, create, edit, search, duplicate handling | Standard CRUD master + search modes | 2 |  |  | Pending
Progbiz ERP | Master | Users | User management (/users) | Create user, assign role, edit, activate/deactivate, login as new user | User creation affects auth; verify with a real login | 3 |  |  | Pending
Progbiz ERP | Master | Users | Reset password (/change-user-password) | Change a user's password, old password invalid, new one logs in | 2-login verification per change | 1.5 |  |  | Pending
Progbiz ERP | Master | Branch | Branch master (/branches) | Create/edit branch, appears in branch dropdowns (task/enquiry forms) | CRUD + cross-module dropdown effect | 1.5 |  |  | Pending
Progbiz ERP | Master | User Role Groups | Role groups & permissions (/user-role-groups) | Create group, permission matrix on/off, menu visibility per role | Permission matrix = many toggle-effect checks with role login | 3 |  |  | Pending
Progbiz ERP | Master | Teams | Teams master (/teams) | Create team, add/remove members, team reflected in task/project assignment | CRUD + effect check in 2 modules | 2 |  |  | Pending
Progbiz ERP | Master | Client Settings | Client settings (/client-setting) | Settings toggles, save, verify each toggle's effect on the app | Each setting needs an effect verification, not just save | 2.5 |  |  | Pending
Progbiz ERP | Master | Custom Fields | Custom/dynamic fields (/dynamic-fields) | Create field per entity, appears on target form, data saves & displays | Field-type matrix (text/date/select) x target forms | 2.5 |  |  | Pending
Progbiz ERP | Master | Dynamic Reports | Dynamic report builder (/dynamic-list) | Create report (Leads/Tasks/Customers/Project), field picker, filters, generate & verify data | 4 report types; builder + output correctness | 3 |  |  | Pending
Progbiz ERP | Master | Field Mapping | Field mapping tags (/field-map-tags) | Create/edit mapping tags, used correctly in templates/reports | Small master; effect check in one consumer | 1.5 |  |  | Pending
Progbiz ERP | Excel Upload | Individual Customer | Individual customer upload (/individual-customer-upload) | Template download, valid file upload, invalid/missing-column file, duplicate rows, data verification in Customers | 5 checks incl. negative files; verify rows landed | 2.5 |  |  | Pending
Progbiz ERP | Excel Upload | Business Customer | Business customer upload (/business-customer-upload) | Same matrix as individual: template, valid, invalid, duplicates, verification | Mirrors individual-customer flow with business fields | 2.5 |  |  | Pending
Progbiz ERP | Excel Upload | Enquiry Upload | Enquiry upload (/enquiry-upload) | Template, valid upload creates leads, invalid rows report, duplicate phone handling, leads visible in CRM listing | Creates CRM data — cross-module verification is slower | 3 |  |  | Pending
Progbiz ERP | Excel Upload | Project Upload | Project upload (/projects-upload) | Template, valid upload, invalid rows, projects visible in Projects list | Cross-check in Project module | 2.5 |  |  | Pending
Progbiz ERP | Excel Upload | Solar Project Upload | Solar project upload (/solar-project-upload) | Template, valid upload, invalid rows, solar projects listed | Variant of project upload with solar fields | 2.5 |  |  | Pending
TOTAL

## Daily Hours Log
Date | Module | Sub-Module | Hours Spent | What was done | Status Update

## Dashboard
WBS DASHBOARD — CRM · Task Management · Master · Excel Upload
By Module
Module | Checks | Completed | Pending/In-Prog | Est Hours | Actual Hours | Variance (h) | % Complete
CRM
Task Management
Master
Excel Upload
TOTAL
Daily hours (from Daily Hours Log)
Today's logged hours:
Total logged hours:
HOW TO USE (daily routine)
1. Each day, add a row in 'Daily Hours Log' per sub-module you worked on (Date, Module, Sub-Module, Hours).
2. Update 'Actual Hours' + 'Date Worked' + 'Status' on the matching WBS Tracker row (add hours cumulatively).
3. Variance auto-calculates (Estimated - Actual); negative = over-estimate risk, raise early.
4. Filter WBS Tracker Status column for Completed vs Pending tracking (it is an Excel Table - use the header filters).
5. Pivot dashboard: Insert > PivotTable > select table 'WBS' > Rows: Module, Sub-Module; Values: Sum of Estimated Hours, Sum of Actual Hours; Filter: Status.
6. For a burndown by day: Insert > PivotTable on table 'DailyLog' > Rows: Date; Values: Sum of Hours Spent.
7. For every NEW incoming module: copy this file, replace rows with the new module's sub-module breakdown BEFORE starting work, and commit the estimate.
Formulas:
Checks = SUMIF(DailyLog[Date],TODAY(),DailyLog[Hours Spent])