## WBS Tracker
Project | Module | Sub-Module | Page / Functionality Check | Scope of Check | Estimation Rationale | Estimated Hours | Actual Hours | Date Worked | Status | Variance (h) | Remarks
Progbiz ERP | HRMS | Core HR | Employee listing (/employees) | List load, Filter panel, incl-archived toggle, columns (Code/Name/Dept/Designation/Status), row actions, drill-down | List + filter matrix; grid starts empty until filtered | 3 |  |  | Pending | 3
Progbiz ERP | HRMS | Core HR | Employee create / edit form | New Employee form: personal, branch/department/designation, contact, joining, mandatory-field negatives, save/cancel | Largest master form in the module; full field matrix + negative paths | 4 |  |  | Pending | 4
Progbiz ERP | HRMS | Core HR | Sections (/sections) | Department-linked section create, inline form + grid, edit, delete, duplicate rejection | Simple inline-form CRUD master | 1.5 |  |  | Pending | 1.5
Progbiz ERP | HRMS | Core HR | Worker Directory (/worker-directory) | Cards view, Org Chart view, department filter, name/designation search | Two non-grid visualisations; org chart needs hierarchy data | 2.5 |  |  | Pending | 2.5
Progbiz ERP | HRMS | Core HR | Salary Revisions (/salary-revisions) | Raise Revision form (employee, effective date, new salary, reason), revision history grid, %-change, approval status | Form + history + routes into the approval chain | 3 |  |  | Pending | 3
Progbiz ERP | HRMS | Core HR | Employee Salary Process (/employee-salary-process) | Branch selection, staff list, Basic/leave/payable computation, narration fields, save | Arithmetic verification per employee; consumes attendance + deductions | 3.5 |  |  | Pending | 3.5
Progbiz ERP | HRMS | Core HR | Employee Deductions (/employee-deduction) | Branch/staff/date/deduction-type typeahead/amount/details, save, Cancel discards | Duplicate element ids (#employee x2) + swal2 validation dialog | 2.5 |  |  | Pending | 2.5
Progbiz ERP | HRMS | Core HR | Employee Remarks (/employee-remark) | Reduced form (branch/employee/date/details), save, cancel | Small form; header falsely reads 'Employee Deduction' (build bug to log) | 1.5 |  |  | Pending | 1.5
Progbiz ERP | HRMS | Core HR | Probation Dashboard (/hrms/probation) | Employees-on-probation grid, Start Probation, review checkpoints, days-left, decision actions | State-dependent; needs employees seeded on probation | 3 |  |  | Pending | 3
Progbiz ERP | HRMS | Core HR | Probation Templates (/hrms/probation-templates) | New Template (duration, checkpoint days, criteria), default/active flags, edit, delete | CRUD master feeding the probation flow | 2 |  |  | Pending | 2
Progbiz ERP | HRMS | Core HR | Probation Report (/hrms/probation-report) | Date-range + outcome filter, Run Report, Export Excel, overdue/decision columns | Filter-first report; export not downloaded, only triggered | 2 |  |  | Pending | 2
Progbiz ERP | HRMS | Core HR | Resigned Employees (/resigned-employees) | List, name filter, columns (date/name/phone/designation/nationality) | Read-only list | 1 |  |  | Pending | 1
Progbiz ERP | HRMS | Core HR | Employee Excel Import (/upload-employee) | Download sample, Excel Rules dialog, valid upload, malformed-file rejection, row-level errors | File-upload path + negative fixtures; slowest to set up | 3 |  |  | Pending | 3
Progbiz ERP | HRMS | Core HR | Letter Templates (/letters/templates) | New Template, merge-fields reference, owner/type/subject, active toggle, edit, delete | CRUD + merge-field token verification | 2.5 |  |  | Pending | 2.5
Progbiz ERP | HRMS | Core HR | Generate Letter (/letters/generate) | Template/employee pick, Preview render, Generate, send-mail option, lands in ESS letters | Cross-module verification into /ess/letters | 3 |  |  | Pending | 3
Progbiz ERP | HRMS | Core HR | My Approvals (/approvals) | Tabs: Awaiting my decision / My requests / History; counts, approve & reject, level/raised-by columns | 3 tabs; needs pending items raised from other sub-modules | 3 |  |  | Pending | 3
Progbiz ERP | HRMS | Core HR | Approval Config (/approval/config) | New workflow (type, name), + Add level chain builder, default flag, Save Workflow, configured list | Chain builder with variable levels; drives every approval path | 3.5 |  |  | Pending | 3.5
Progbiz ERP | HRMS | Core HR | Deduction & Remark Reports | /employee-deduction-report + /employee-remark-report: assignee & period filters, View Report | 2 filter-first report pages; empty until queried | 2 |  |  | Pending | 2
Progbiz ERP | HRMS | Recruitment & Onboarding | Job Requisitions (/requisition-list) | New Requisition (designation, department, positions, type, work type, branch), status, designation search | Create form + list filters; feeds the whole hiring funnel | 2.5 |  |  | Pending | 2.5
Progbiz ERP | HRMS | Recruitment & Onboarding | Job Board / Hiring (/vacancy-list) | Add Job Opening, status filter, published/total counters, tab strip to Candidates & Talent Pools | Tabs are router links (leave the page) — verified navigation targets | 3 |  |  | Pending | 3
Progbiz ERP | HRMS | Recruitment & Onboarding | Public careers page (/current-openings) | 'Join Our Team' listing, opening selector, apply entry point, unauthenticated access check | Public page; needs a published opening seeded to exercise apply | 2 |  |  | Pending | 2
Progbiz ERP | HRMS | Recruitment & Onboarding | Job Applications (/job-applications-list) | Applicant grid, details view, Schedule Interview action, Reject action, status transitions | Row actions mutate candidate state; needs applications seeded | 2.5 |  |  | Pending | 2.5
Progbiz ERP | HRMS | Recruitment & Onboarding | Candidates register (/candidates) | Status buckets New/In Progress/Shortlisted/Selected/Rejected with live counts, search, branch/designation filters | 5 buckets x count integrity vs grid | 3 |  |  | Pending | 3
Progbiz ERP | HRMS | Recruitment & Onboarding | Candidate create form (/candidate/0) | Routed form: name/email/phone (+country code)/WhatsApp, branch, user type, status, skills multi-select, résumé upload | Routed page (not a modal); file upload + multi-select | 3.5 |  |  | Pending | 3.5
Progbiz ERP | HRMS | Recruitment & Onboarding | Assessments (/assessment-list) | New Assessment (title, type, description, max score, attachment), library list, edit, delete | CRUD + attachment | 2 |  |  | Pending | 2
Progbiz ERP | HRMS | Recruitment & Onboarding | Interview Schedules (/interview-schedules) | Schedule Interview (candidate, round, datetime, mode), status, reschedule, cancel | Depends on interview-round master + candidates | 2.5 |  |  | Pending | 2.5
Progbiz ERP | HRMS | Recruitment & Onboarding | Offers (/offer-list) | New Offer (candidate, total CTC, joining date), status lifecycle, accept/decline | Gateway from selection to onboarding | 2.5 |  |  | Pending | 2.5
Progbiz ERP | HRMS | Recruitment & Onboarding | Recruitment Pipeline (/recruitment-pipeline) | Kanban board, mandatory vacancy filter, Configure Stages inline editor, Score, auto-sync toggle, card drag between stages | Kanban drag-drop + inline stage editor; heaviest UI in the module | 4.5 |  |  | Pending | 4.5
Progbiz ERP | HRMS | Recruitment & Onboarding | Communication Templates (/communication-templates) | New Template (name, type, subject, body), list, edit, delete, use in candidate comms | CRUD master | 2 |  |  | Pending | 2
Progbiz ERP | HRMS | Recruitment & Onboarding | Talent Pool (/talent-pool) | Name/email search, skill & pool filters, tags, score, archive/restore actions | Search-driven list; archive path from rejected candidates | 2 |  |  | Pending | 2
Progbiz ERP | HRMS | Recruitment & Onboarding | Recruitment settings | /candidate-status (status + nature) and /interview-rounds (round + order): create, reorder, edit, delete | 2 small masters that drive the funnel stages | 2 |  |  | Pending | 2
Progbiz ERP | HRMS | Recruitment & Onboarding | Onboarding Templates (/onboarding-templates) | New Template, joining checklist items, defaults, edit, delete | CRUD master feeding onboarding runs | 2 |  |  | Pending | 2
Progbiz ERP | HRMS | Recruitment & Onboarding | Onboarding Pipeline (/onboarding-pipeline) | Start Onboarding wizard from an accepted offer, checklist progress, completion -> employee record | Cross-module: ends by creating an employee | 2.5 |  |  | Pending | 2.5
Progbiz ERP | HRMS | Attendance & Time | Shifts & Rules (/shifts) | New Shift (name, type, timing, night-shift flag), active toggle, shift-name search, edit, delete | Master that every attendance calculation depends on | 3 |  |  | Pending | 3
Progbiz ERP | HRMS | Attendance & Time | Shift Roster (/shift-roster) | Assign shift by scope (Branch/Department/Employee/Company), date range, current assignments grid, active-only filter | Scope cascade x4; filters live in the offcanvas panel | 3.5 |  |  | Pending | 3.5
Progbiz ERP | HRMS | Attendance & Time | Attendance Log (/attendance-log) | Filter-first report: worked/OT/balance/must-work hours, entry-exit, session details, employee status | 15 columns; grid empty until filters applied | 3 |  |  | Pending | 3
Progbiz ERP | HRMS | Attendance & Time | Data from Device (/data-from-device) | Biometric punch feed: punch type, recognition type, registered-in-system flag, device, sync time, image | Device-fed data; needs punches seeded to assert | 2.5 |  |  | Pending | 2.5
Progbiz ERP | HRMS | Attendance & Time | Add Visit Report (/add-visit-report) | Field-visit punches: check-in/out, purpose, site name, site image, mobile location | Geo + image columns; header misspelt 'Add Vist Report' (bug to log) | 2.5 |  |  | Pending | 2.5
Progbiz ERP | HRMS | Attendance & Time | Regularization (/regularization) | Raise correction (employee, date, type, in/out datetime, reason, attachment), request queue, approve/reject | Create + approval queue + file attach; ESS raises into the same queue | 3.5 |  |  | Pending | 3.5
Progbiz ERP | HRMS | Attendance & Time | Overtime Approval (/overtime-approval) | OT queue: minutes, eligibility, payout, exported flag, approve/reject, search + date range | Approval path feeding payroll; offcanvas filters | 3 |  |  | Pending | 3
Progbiz ERP | HRMS | Attendance & Time | Attendance Finalization (/attendance-finalization) | Start/refresh pay-cycle run, period/scope/target/cut-off, pending count, Finalize, run history | State-mutating pay-cycle gate; must not finalize real periods in tests | 4 |  |  | Pending | 4
Progbiz ERP | HRMS | Attendance & Time | Geofences (/geofences) | Add Location (scope, applies-to, lat/long, radius), status, activate/deactivate, search | Map-backed coordinates; receives approved ESS locations | 3 |  |  | Pending | 3
Progbiz ERP | HRMS | Attendance & Time | Timesheet (/timesheet) | Attendance hours vs task hours comparison, employee search, date range, shift/status filters | Cross-module reconciliation vs Task Management | 2.5 |  |  | Pending | 2.5
Progbiz ERP | HRMS | Attendance & Time | Attendance Report Pack (/attendance-report-pack) | Daily register, report-type/branch/department/employee filters, date range, Export, Previous/Next paging | Multi-report pack with paging; export triggered not downloaded | 3 |  |  | Pending | 3
Progbiz ERP | HRMS | Attendance & Time | Operation approval (+report) | /approval-operation and /approval-operation-report: worked/OT/balance hours approval, late/early minutes, fixed hours, remarks | 2 pages; hour-arithmetic verification | 3 |  |  | Pending | 3
Progbiz ERP | HRMS | Attendance & Time | Absent approval (+report) | /approval-absent and /approval-absent-report: absence approval by period, must-work hours, fixed hours, remarks, delete | 2 pages; mirrors the operation pair | 3 |  |  | Pending | 3
Progbiz ERP | HRMS | Leave Management | Leave Types (/leave-types) | Create type, half-day support flag, document-required flag, edit, delete, duplicate rejection | Root master of the leave chain | 2 |  |  | Pending | 2
Progbiz ERP | HRMS | Leave Management | Leave Patterns (/leave-patterns) | New pattern, per-type entitlement details, edit, delete | Depends on leave types | 2 |  |  | Pending | 2
Progbiz ERP | HRMS | Leave Management | Leave Policy (/leave-policy) | Choose a leave pattern, policy configuration, save, effect on assignments | Config page linking pattern -> policy | 2 |  |  | Pending | 2
Progbiz ERP | HRMS | Leave Management | Leave Assignment (/leave-assignment-list) | New assignment (type: branch/department/employee), target, pattern, Filter, edit, delete | Assignment matrix drives every employee's entitlement | 2.5 |  |  | Pending | 2.5
Progbiz ERP | HRMS | Leave Management | Leave Request (/leave-request-list) | New Leave Request (type, start/end, half-day, remarks), list, approval status, edit/cancel rules | Admin-side request creation; mirrors ESS apply | 2.5 |  |  | Pending | 2.5
Progbiz ERP | HRMS | Leave Management | Leave Approval (/leave-approval) | Worklist, 3 filter selects, row select + Approve/Reject Selected (bulk), Clear, Delegate approvals modal | Bulk decisions + delegation modal; posts to ledger & balances | 4 |  |  | Pending | 4
Progbiz ERP | HRMS | Leave Management | My Leave Policy (/my-leave-policy) | Year selector, Show, policy entitlement display for the logged-in user | Read-only personal view | 1.5 |  |  | Pending | 1.5
Progbiz ERP | HRMS | Leave Management | Leave Balances (/leave-balances) | Year, Show, Run Accrual, columns Opening/Accrued/Carried-Fwd/Used/Encashed/Reserved/Available/Liability | Accrual engine trigger + 10-column arithmetic | 3.5 |  |  | Pending | 3.5
Progbiz ERP | HRMS | Leave Management | Leave Ledger (/leave-ledger) | Append-only txn history, employee/type/date filters (offcanvas), balance-after integrity, Export | Append-only guarantee + running-balance verification | 3 |  |  | Pending | 3
Progbiz ERP | HRMS | Leave Management | Leave / Attendance Sync (/leave-attendance-sync) | Year & period filters, sync status, LOP flags, attendance rows touched, Recalculate period | Recalculation is state-mutating — assert read-only paths only | 3 |  |  | Pending | 3
Progbiz ERP | HRMS | Leave Management | Leave Encashment (/leave-encashment) | Request encashment (type, days, amount), my-requests list, status | Request side; feeds payroll | 2 |  |  | Pending | 2
Progbiz ERP | HRMS | Leave Management | Encashment Approval (/leave-encashment-approval) | 5 filter selects, request grid, approve/reject, amount verification | Approval side of encashment | 2.5 |  |  | Pending | 2.5
Progbiz ERP | HRMS | Leave Management | Leave Delegation (/leave-delegation) | Active & past delegations registry, from/to, date range, active flag | Created from Leave Approval; read-heavy registry | 2 |  |  | Pending | 2
Progbiz ERP | HRMS | Leave Management | Employee Handover (/employee-handover) | Set up handover (from/to employee, dates, covers), active flag, all-handovers grid, edit, delete | Admin twin of the ESS handover page | 2.5 |  |  | Pending | 2.5
Progbiz ERP | HRMS | Leave Management | Comp-Offs (/comp-offs) | Request Comp-Off, earned/source/days/expiry, my credits grid, status | Employee-facing credit request | 2 |  |  | Pending | 2
Progbiz ERP | HRMS | Leave Management | Comp-Off Management (/comp-off-management) | All-employee credits, pending-only toggle, Grant / Reject per row, expiry handling | Per-row grant/reject; only present when rows exist | 2.5 |  |  | Pending | 2.5
Progbiz ERP | HRMS | Leave Management | Holidays (/holiday-list) | New Holiday (name, dates, calendar), search, Export, Calendar view at /holiday-calendar | CRUD + separate calendar route | 2.5 |  |  | Pending | 2.5
Progbiz ERP | HRMS | Leave Management | Holiday Assignment (/holiday-assignment-list) | New assignment (type, target), Filter, list, edit, delete | Assignment matrix for holiday calendars | 2 |  |  | Pending | 2
Progbiz ERP | HRMS | Leave Management | Leave Reports (/leave-reports) | Register / Balance / Utilization report switch, year & branch & department filters, Filter | 3 report modes behind one page | 3 |  |  | Pending | 3
Progbiz ERP | HRMS | Leave Management | Absence Analytics (/absence-analytics) | Monthly trend, absence rate by department, Bradford Factor risk table (Spells/Days/Score/Signal), filters | Charts + Bradford scoring; collapses to 'No analytics available' with no data | 3 |  |  | Pending | 3
Progbiz ERP | HRMS | Leave Management | Leave Calendar (/leave-calendar) | Month/branch/department view, employee-name filter, Show, leave markers on calendar | Calendar visualisation, not a grid | 2 |  |  | Pending | 2
Progbiz ERP | HRMS | My Workspace (ESS) | ESS Dashboard (/ess) | KPI tiles (Leave Available / Today's Attendance / Pending Requests / Letters to Acknowledge), profile card, Quick Actions, Upcoming Holidays, Birthdays | Async-loading widgets; KPI values must reconcile with source pages | 2.5 |  |  | Pending | 2.5
Progbiz ERP | HRMS | My Workspace (ESS) | My Profile (/ess/profile) | Read-only overview (code/branch/department/designation/reports-to/joined), Request A Change form (name/email/ID/passport/blood group + reason), Submit Change Request | Write path is an approval request, not a direct edit | 3 |  |  | Pending | 3
Progbiz ERP | HRMS | My Workspace (ESS) | My Requests (/ess/requests) | Profile change request list, status tracking, documented empty state | Round-trip verification target for /ess/profile | 1.5 |  |  | Pending | 1.5
Progbiz ERP | HRMS | My Workspace (ESS) | My Leave (/ess/leave) | Balances table (Balance/Reserved/Available), Apply For Leave (type, from/to, half-day, reason), my requests, year Show | Primary ESS->admin E2E: apply -> approve -> ledger/balance | 3 |  |  | Pending | 3
Progbiz ERP | HRMS | My Workspace (ESS) | My Handover (/my-handover) | Set Up Handover (assignee, dates, covers, reason), Save, Clear, my-handovers grid | Self-service twin of admin handover | 2 |  |  | Pending | 2
Progbiz ERP | HRMS | My Workspace (ESS) | My Attendance (/ess/attendance) | Date-range Show, history grid (entry/exit/worked/OT/status), Regularize, Raise OT | Raises into admin regularization & OT queues | 3 |  |  | Pending | 3
Progbiz ERP | HRMS | My Workspace (ESS) | My Locations (/ess/locations) | Add work location (name, radius; lat/long are map-set read-only), address search, Use my location, Submit for approval, my-locations grid | Google-Maps widget; geolocation not grantable headless; grid paints below the map | 3.5 |  |  | Pending | 3.5
Progbiz ERP | HRMS | My Workspace (ESS) | My Documents (/ess/documents) | Upload A Document (type, number, category, expiry, file), documents grid, expiry status | File-upload path with expiry tracking | 2.5 |  |  | Pending | 2.5
Progbiz ERP | HRMS | My Workspace (ESS) | My Letters (/ess/letters) | Request a letter/certificate, published letters grid, acknowledge action, KPI decrement | Acknowledge flips state and the dashboard KPI | 2 |  |  | Pending | 2
Progbiz ERP | HRMS | My Workspace (ESS) | My Pay (/ess/payslips) | Year Show, payslip grid (Period/Basic/Deductions/Net/Payable/Paid), PDF-unavailable footnote | Terminal assertion of the payroll chain | 2 |  |  | Pending | 2
Progbiz ERP | HRMS | My Workspace (ESS) | My Probation (/ess/probation) | Probation status panel, review checkpoints, documented not-on-probation state | Read-only mirror of admin probation | 1.5 |  |  | Pending | 1.5
Progbiz ERP | HRMS | Cross-Cutting | Login & session | Company-code/username/password form, invalid-credential negatives, session persistence, logout, redirect-to-login on expiry | Gate for every other check; 3-field tenant login | 2 |  |  | Pending | 2
Progbiz ERP | HRMS | Cross-Cutting | Navigation & menu integrity | HRMS menu tree (Core HR / Recruitment / Attendance / Leave / ESS groups), every route reachable, breadcrumb correctness | 80 routes to walk; catches broken/removed menu entries | 2.5 |  |  | Pending | 2.5
Progbiz ERP | HRMS | Cross-Cutting | Approval workflow E2E | Config a chain then drive leave, salary revision, regularization, encashment and ESS profile-change through /approvals to completion | Multi-module chain; the highest-value regression path | 4 |  |  | Pending | 4
Progbiz ERP | HRMS | Cross-Cutting | Test data seeding & environment | Employees, shifts+roster, leave types/patterns/policy/assignment, holidays, requisition->opening->candidate, probation records | Prerequisite for most state-dependent checks; done once per environment | 3 |  |  | Pending | 3
Progbiz ERP | HRMS | Cross-Cutting | Defect logging & retest | Log build bugs found (remark header, 'Add Vist Report' typo, upload-employee stray card title), retest after fixes | Known issues already observed during the study | 2.5 |  |  | Pending | 2.5
[5 empty] | TOTAL | 217 | 0

## Daily Hours Log
Date | Module | Sub-Module | Hours Spent | What was done | Status Update

## Dashboard
WBS DASHBOARD — HRMS (Core HR · Recruitment · Attendance · Leave · ESS)
By Sub-Module
Sub-Module | Checks | Completed | Pending/In-Prog | Est Hours | Actual Hours | Variance (h) | % Complete
Core HR | 18 | 0 | 18 | 46.5 | 0 | 46.5 | 0%
Recruitment & Onboarding | 15 | 0 | 15 | 38.5 | 0 | 38.5 | 0%
Attendance & Time | 13 | 0 | 13 | 39.5 | 0 | 39.5 | 0%
Leave Management | 21 | 0 | 21 | 52 | 0 | 52 | 0%
My Workspace (ESS) | 11 | 0 | 11 | 26.5 | 0 | 26.5 | 0%
Cross-Cutting | 5 | 0 | 5 | 14 | 0 | 14 | 0%
TOTAL | 83 | 0 | 83 | 217 | 0 | 217 | 0%
Daily hours (from Daily Hours Log)
Today's logged hours: | 0
Total logged hours: | 0
HOW TO USE (daily routine)
1. Each day, add a row in 'Daily Hours Log' per sub-module you worked on (Date, Module, Sub-Module, Hours).
2. Update 'Actual Hours' + 'Date Worked' + 'Status' on the matching WBS Tracker row (add hours cumulatively).
3. Variance auto-calculates (Estimated - Actual); negative = over-estimate risk, raise early.
4. Filter the WBS Tracker Status column for Completed vs Pending (it is an Excel Table - use the header filters).
5. Pivot: Insert > PivotTable > table 'WBS_HRMS' > Rows: Sub-Module, Page; Values: Sum of Estimated/Actual Hours.
6. Burndown by day: Insert > PivotTable on table 'DailyLogHRMS' > Rows: Date; Values: Sum of Hours Spent.
7. Estimates assume the config chain is seeded first (shifts+roster, leave types->pattern->policy->assignment,
holidays, requisition->opening->candidate) - see the 'Test data seeding' row under Cross-Cutting.
Formulas:
Checks = SUMIF(DailyLogHRMS[Date],TODAY(),DailyLogHRMS[Hours Spent])